## Slide 1
CSRA FS Automation Project
Standardizing and automating the CSRA fee schedule process to improve accuracy, efficiency, and scalability.
Objective
Standardize and automate the CSRA fee schedule process across CMS state file download, SOP review and update, master file / QNXT validation, data-load preparation, and latest fee update in QNXT.
Top-Level Metrics / Summary
99
Total Segments
30
R2 Segments Released
34
R1 Pilot Segments
12
R5 Segments in QA
Risks / Issues / Assumptions / Opportunities / Dependencies
Area
Description
Mitigation / Next Steps
Status
FL / OK and Release 4 items await business review or results confirmation.
Complete business review and confirm approved items for QNXT load.
Business Review
Pending
Release 2: 30 segments show completed deployment and business approval.
Confirm QNXT load completion for the approved items.
Release 2
Completed
Release 3 has mixed status: FL / OK review pending; WV development underway.
Complete WV development and close pending FL / OK reviews.
Release 3
In Progress
Release 5: 12 segments in QA across OHRS / MD; some QA files need attention.
Resolve file gaps and complete testing against the 28 Oct target.
Release 5
In Progress
Milestones
Key Milestone
Date / Status
MI POC foundation – PROD deployment and first run completed
07/15/2026
Completed
38 MI FS files live and 300K+ records validated
July 2026
Completed
Release 2: 30 segments deployed and business approved
22 Oct status
Completed
Release 1: 34 pilot segments; production target 13 Nov
13 Nov 2026
In Progress
Release 3: 13 segments; review / development in progress
30 Oct / varies
In Progress
Release 4: 10 segments in review; Release 5: 12 in QA
30 Oct target
In Progress
Accomplishments / In Progress / Next Steps
Accomplishments
• MI POC foundation deployed successfully.
• Release 2: 30 segments deployed and business approved.
• Current tracker scope totals 99 segments.
In Progress
• Release 1: 34 pilot segments in development.
• Release 3: 13 segments in development / review.
• Release 4: 10 segments awaiting review.
• Release 5: 12 segments in QA; target 28 Oct.
Next Steps
• Close pending business reviews and confirm QNXT load.
• Complete WV development and Release 5 testing.
• Resolve missing or outdated QA files.
• Track 30 Oct and 13 Nov deployment targets.
Status as of 22 Oct 2026:
Segment totals: R1 34, R2 30, R3 13, R4 10, R5 12 = 99. Scope totals do not imply completed release. Dates are targets.
Notes: Updated from supplied Planwise status screenshots dated 22 October 2026. Total Segments summed by release: R1 rows 2–4 = 7+20+7 = 34; R2 rows 5–32 = 27 single-segment rows plus one 3-segment row = 30; R3 rows 33–40 = 7 single-segment rows plus one 6-segment row = 13; R4 rows 41–47 = 6 single-segment rows plus one 4-segment row = 10; R5 rows 48–52 = 1+1+3+3+4 = 12. Total scope = 99 segments. R2 deployment and business approval completed. Other scope totals do not imply release completion. File counts are not inferred from segment counts. Historic July POC milestone retained from supplied deck. Layout and images preserved.