## Slide 1
CSRA FS Automation Project
Standardizing and automating the CSRA fee schedule process to improve accuracy, efficiency, and scalability.
Objective
Standardize and automate the CSRA fee schedule process across CMS state file download, SOP review and update, master file / QNXT validation, data-load preparation, and latest fee update in QNXT.
Top-Level Metrics / Summary
38
MI Files Live
300K+
Records Validated
35
August Files
124
2026 Files
Risks / Issues / Assumptions / Opportunities / Dependencies
Area
Description
Mitigation / Next Steps
Status
Final business review and QNXT load confirmation remain a dependency for completed build items.
Complete review and confirm QNXT load for approved items.
Dependency
Dependency
Release 2 deployment depends on review completion for MI + IL/ILC files.
Continue review process and address open items.
Release 2
In Progress
Release 3 rollout is in build progress for VA, FL, OK, and WV plans.
Continue build development and prepare for September deployment.
Release 3
In Progress
Standardized deployment, validation, and monitoring framework creates opportunity to scale future file onboarding.
Leverage framework to onboard additional state files in 2026 and beyond.
Opportunity
On Track
Milestones
Key Milestone
Date / Status
MI POC foundation – PROD deployment and first run completed
07/15/2026
Completed
38 MI FS files live and 300K+ records validated
July 2026
Completed
Release 2: MI + IL/ILC delivery (3 plans | 25 Fee IDs | 35 files)
August 2026
Review in Progress
Production deployment target for August files
08/31/2026
On Track
Release 3 rollout: VA, FL, OK + WV (4 plans | 13 Fee IDs | 19 files)
September 2026
Build in Progress
2026 delivery roadmap covers 124 files
2026
On Track
Accomplishments / In Progress / Next Steps
Accomplishments
• MI POC foundation deployed successfully.
• 38 MI FS files are live.
• 300K+ records have been validated.
• Standard deployment, validation, and monitoring framework created.
In Progress
• Controlled execution feedback incorporated.
• Business final review underway; QNXT load after confirmation.
• Release 2 review process in progress.
• Release 3 build development in progress.
Next Steps
• Complete review and deploy August files.
• Finalize QNXT load for approved items.
• Continue September rollout for VA, FL, OK, and WV.
• Execute against the broader 2026 roadmap.
2026 Delivery Roadmap:
Covers 124 files across multiple states, with phased deployments through September 2026 and a standardized framework for future file onboarding.