## Slide 1
CSRA FS Automation Project Status Update
Executive delivery roadmap | 2026
Pilot proven; three releases establish the path to scaled automation
AUTOMATION SCOPE
CMS / state file download → SOP review & update → Master file / QNXT validation → data-load preparation → latest fee update in QNXT
38
MI FILES LIVE
300K+
RECORDS VALIDATED
35
AUGUST FILES
124
2026 FILES
PILOT • JULY
LIVE + HYPERCARE
MI POC foundation
• PROD deployment and first run: 07/15
• 38 MI FS files; 300K+ records validated
• Standard deployment, validation and monitoring framework created
• Controlled-execution feedback incorporated
• Business final review; QNXT load after confirmation
• Release 2 initiated: additional MI Fee IDs + IL/ILC (11 files)
RELEASE 2 • AUGUST
REVIEW IN PROGRESS
MI + IL/ILC delivery
• 3 plans | 25 Fee IDs | 35 files
• MI additional files and IL/ILC plans
• Build development completed
• Review process in progress
• Production deployment target: 08/31
RELEASE 3 • SEPTEMBER
BUILD IN PROGRESS
VA, FL, OK + WV rollout
• 4 plans | 13 Fee IDs | 19 files
• Build development in progress
• Production deployment target: end of September
2026 DELIVERY ROADMAP
12 plans • 58 Fee IDs • 124 files
Portfolio shown in source roadmap: MI (Pilot), MI, IL (ABH IL), IL (IL Duals), VA, FL, OK, WV, NJ, LA, NY, OHRIse and MD
DELIVERY PHASES
1
CONFIGURATION
+ DEVELOPMENT
2
QA TESTING
3
UAT DEMO
4
GO-LIVE
©2026 CVS Health and/or one of its affiliates. Confidential and proprietary.
Notes: This slide consolidates the three supplied project-status slides into one executive view. All non-crossed narrative items, dates, counts, statuses, milestones, portfolio names and roadmap phases were audited against the source screenshots. The Files Automated table and the Release 2 Fee ID detail tables were excluded because the manager crossed them out.
[Sources]
- User-provided screenshots of CSRA FS Automation Project Status Update slides and manager feedback, September 2026.